## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1 | Comment2
3636943 | 68227 | ATM Project | 1 | ATM_1-1 | 292216 | Bug |  |  | 63738 | 1.0 | No option for savings account in balance Inquiry | 1. Function being tested: Balance Inquiry Option. 2. Initial state of the System: ATM machine is ON, customer has pressed option 4 for the Balance Inquiry using Card Number: 1 3. Steps to reproduce the defect/bug 1. Select Option 4 for the Balance Inquiry 4. Expected Outcome: The ATM machine should display Checking, Savings account and Money Market account. 5. Actual Outcome: The ATM machine actually shows Checking and Money Market Account on the ATM machine display. | 3 | Resolved | 3 | Normal |  |  |  |  | 319528 | LAB1-Group23 | 319528 | LAB1-Group23 | Jan. 20, 2022 12:16 |  | 319528 | LAB1-Group23 | Jan. 22, 2022 15:57 | 0 | 0 | Jan. 21, 2022 18:19 LAB1-Group23 Defect has been resolved in version 1.1 but still exists in version 1.0
3636948 | 68227 | ATM Project | 2 | ATM_1-2 | 292216 | Bug |  |  | 63738 | 1.0 | Balance checking on Money Market account shows an error. | 1. The function being tested: Balance Inquiry 2. The initial state: System is on and idle 3. Steps to reproduce the bug: turn on system -> insert card #2 -> choose balance inquiry -> choose money market 4. Expected outcome: show the balance $5000 5. Actual output: It shows invalid account type. | 3 | Resolved | 3 | Normal |  |  |  |  | 319537 | Tianfan Zhou | 319528 | LAB1-Group23 | Jan. 20, 2022 12:20 |  | 319538 | Girimer Singh | Jan. 27, 2022 11:53 | 0 | 0 | Jan. 21, 2022 18:17 LAB1-Group23 Defect has been resolved in version 1.1 but still exists in version 1.0 | Jan. 27, 2022 11:53 Girimer Singh fixed in version 1.1
3636954 | 68227 | ATM Project | 3 | ATM_1-3 | 292216 | Bug |  |  | 63738 | 1.0 | Error in the Balance Inquiry in the the Checking Account | 1. Function being tested: Balance Inquiry Option. 2. Initial state of the System: ATM machine is ON, customer has pressed option 4 for the Balance Inquiry using Card Number: 2 3. Steps to reproduce the defect/bug 1. Select Option 4 for the Balance Inquiry 2. Select Option 1 for the checking 4. Expected Outcome: The ATM machine should display only Checking account balance only. 5. Actual Outcome: When a user presses 3 or any other button except 1 and 2 on the balance checking menu, it dispenses $20 from the any random account. | 2 | In Progress | 3 | Normal |  |  |  |  | 319538 | Girimer Singh | 319528 | LAB1-Group23 | Jan. 20, 2022 12:22 |  | 319538 | Girimer Singh | Jan. 22, 2022 15:11 | 0 | 0 | Jan. 21, 2022 18:15 LAB1-Group23 Defect still exists in version 1.1 when option 3 is pressed only.
3636968 | 68227 | ATM Project | 5 | ATM_1-5 | 292216 | Bug |  |  | 63738 | 1.0 | Error on the Transfer Menu | 1. The function being tested: Transfer 2. The initial state: System is on and customer has inserted card # 1 3. Steps to reproduce the bug: 1. Turn on system 2. Insert card #1 3. Transfer 4. Expected outcome: Option 4-9 and 0 should not dispense any money or do any other action 5. Actual output: When a user presses any button except 1, 2 and 3 on the Num-pad, The machine dispenses $20 from any random account. | 2 | In Progress | 3 | Normal |  |  |  |  | 319538 | Girimer Singh | 319528 | LAB1-Group23 | Jan. 20, 2022 12:30 |  | 319528 | LAB1-Group23 | Jan. 21, 2022 18:24 | 0 | 0 | Jan. 21, 2022 18:24 LAB1-Group23 Defect still exists in version 1.1 when the user presses the option 4 only.
3636977 | 68227 | ATM Project | 6 | ATM_1-6 | 292216 | Bug |  |  | 63738 | 1.0 | Incorrect amount transferred | 1. The function being tested: Transfer 2. The initial state: System is on and idle 3. Steps to reproduce the bug: turn on system -> insert card #1 -> transfer -> checking -> saving -> 100 4. expected outcome: transfers $100 from checking to savings 5. actual output: It only transfers $99.50 to the savings account. | 3 | Resolved | 3 | Normal |  |  |  |  | 319537 | Tianfan Zhou | 319528 | LAB1-Group23 | Jan. 20, 2022 12:35 |  | 319537 | Tianfan Zhou | Jan. 22, 2022 15:49 | 0 | 0 | Jan. 21, 2022 18:10 LAB1-Group23 Defect has been resolved in version 1.1 but still exists in version 1.0
3637649 | 68227 | ATM Project | 7 | ATM_1-7 | 292216 | Bug |  |  | 63738 | 1.0 | Incorrect Card Number on the Receipt | 1. The function being tested: Balance Inquiry 2. The initial state: System is on and customer has inserted card # 1 3. Steps to reproduce the bug: 1. Turn on system 2. Insert card #1 3. Balance Inquiry 4. Expected outcome: The ATM machine should print the receipt with Card Number 1 it. 5. Actual output: The ATM machine prints receipt with Card 2 on it. | 2 | In Progress | 3 | Normal |  |  |  |  | 319538 | Girimer Singh | 319528 | LAB1-Group23 | Jan. 20, 2022 20:20 |  | 319528 | LAB1-Group23 | Jan. 21, 2022 18:03 | 0 | 0 | Jan. 21, 2022 18:03 LAB1-Group23 Defect still exists in version 1.1
3637651 | 68227 | ATM Project | 8 | ATM_1-8 | 292216 | Bug |  |  | 63738 | 1.0 | Incorrect amount on depositing money to saving account | 1. The function being tested: Deposit 2. The initial state: System is on and idle 3. Steps to reproduce the bug: turn on system -> insert card #1 -> deposit->saving ->100 4.expected outcome: deposit $100 into saving account, balance will be $1100 5.actual output: It only deposit $90, new balance is $1090 | 2 | In Progress | 3 | Normal |  |  |  |  | 319537 | Tianfan Zhou | 319537 | Tianfan Zhou | Jan. 20, 2022 20:20 |  | 319528 | LAB1-Group23 | Jan. 27, 2022 11:31 | 0 | 0 | Jan. 21, 2022 18:06 LAB1-Group23 Defect still exists in version 1.1 and it deducts $0.10 on each deposit.
3637667 | 68227 | ATM Project | 9 | ATM_1-9 | 292216 | Bug |  |  | 63738 | 1.0 | Incorrect amount when depositing money to MMKT | 1. The function being tested: Deposit 2. The initial state: System is on and idle 3. Steps to reproduce the bug: turn on system -> insert card #2 ->deposit -> MMKT->100 4.expected outcome: deposit $100 to MMKT, new balance will be $5100 5.actual output: It only deposit $90 to MMKT, new balance is $5090 | 2 | In Progress | 3 | Normal |  |  |  |  | 319537 | Tianfan Zhou | 319537 | Tianfan Zhou | Jan. 20, 2022 20:25 |  | 319528 | LAB1-Group23 | Jan. 26, 2022 17:21 | 0 | 0 | Jan. 21, 2022 18:02 LAB1-Group23 Defect still exists in version 1.1 an deducts $0.10 on each new deposit.
3637684 | 68227 | ATM Project | 10 | ATM_1-10 | 292216 | Bug |  |  | 63738 | 1.0 | Error in the transferring money between accounts | 1. The function being tested: Transfer 2. The initial state: System is on and idle 3. Steps to reproduce the bug: turn on system -> insert card #2 -> transfer -> checking -> MMRT -> 100 4.expected outcome: after the transfer transaction, new balance on should be $5100 5.actual output: It deducts $0.50 on each transfer transaction and only $99.50 get transferred. | 3 | Resolved | 3 | Normal |  |  |  |  | 319537 | Tianfan Zhou | 319537 | Tianfan Zhou | Jan. 20, 2022 20:31 |  | 319528 | LAB1-Group23 | Jan. 26, 2022 17:41 | 0 | 0 | Jan. 21, 2022 18:00 LAB1-Group23 Defect has been resolved in version 1.1 but still exists in version 1.0
3637728 | 68227 | ATM Project | 11 | ATM_1-11 | 292216 | Bug |  |  | 63738 | 1.0 | Incorrect From and To Fields in the Transfer Money Receipt | 1. The function being tested: Transfer 2. The initial state: System is on and customer has inserted card # 1 3. Steps to reproduce the bug: 1. Turn on system 2. Insert card #1 3. Transfer 4. Checking 4. Expected outcome: Printed Receipt should have From: CHKG and To: SVGS 5. Actual output: Printed Receipt have From: SVGS and To: CHKG | 2 | In Progress | 3 | Normal |  |  |  |  | 319528 | LAB1-Group23 | 319528 | LAB1-Group23 | Jan. 20, 2022 20:39 |  | 319528 | LAB1-Group23 | Jan. 21, 2022 17:57 | 0 | 0 | Jan. 21, 2022 17:57 LAB1-Group23 Defect still exists in version 1.1
3638091 | 68227 | ATM Project | 12 | ATM_1-12 | 292216 | Bug |  |  | 63738 | 1.0 | MFT - Incorrect Withdrawal amount | 1. The function being tested: Withdrawal 2. The initial state: System is on and customer has inserted card # 1 3. Steps to reproduce the bug: 1. Turn on system 2. Insert card #1 3. Withdrawal 4. Checking 5. Select $20 from the Menu 4. Expected outcome: Withdraws $20 from the checking account. 5. Actual output: Withdraws $40 from the checking account. | 3 | Resolved | 3 | Normal |  |  |  |  | 319528 | LAB1-Group23 | 319528 | LAB1-Group23 | Jan. 20, 2022 22:42 |  | 319528 | LAB1-Group23 | Jan. 21, 2022 17:39 | 0 | 0 | Jan. 21, 2022 17:39 LAB1-Group23 Defect has been resolved in version 1.1 and it still exists in version 1.0
3639681 | 68227 | ATM Project | 14 | ATM_1-14 | 292216 | Bug |  |  | 63738 | 1.0 | MFT - Invalid key Extension (1st time) | 1.The function being tested: Invalid key extension 2.The initial state: After input incorrect password, Request to re-enter PIN is being displayed 3.Steps to reproduce the bug: turn on system -> insert card #1 -> input incorrect password -> input correct password 4.expected outcome: Original transaction completes successfully 5.actual output: Transaction unsuccessful, after enter the correct key, system asks to enter the key again. | 2 | In Progress | 3 | Normal |  |  |  |  | 319537 | Tianfan Zhou | 319537 | Tianfan Zhou | Jan. 21, 2022 08:01 |  | 319537 | Tianfan Zhou | Jan. 26, 2022 17:37 | 0 | 0 | Jan. 21, 2022 18:16 LAB1-Group23 Defect still exists in version 1.1
3639701 | 68227 | ATM Project | 15 | ATM_1-15 | 292216 | Bug |  |  | 63738 | 1.0 | MFT - Invalid PIN Extension (2nd time) | 1. The function being tested: Invalid key extension 2. The initial state: After input incorrect password, Request to re-enter PIN is being displayed 3. Steps to reproduce the bug: turn on system -> insert card #1 -> input incorrect password -> input incorrect password -> input correct password 4. expected outcome: Original transaction completes successfully 5. actual output: Transaction unsuccessful, after enter the correct key, system asks to enter the key again. | 2 | In Progress | 3 | Normal |  |  |  |  | 319537 | Tianfan Zhou | 319537 | Tianfan Zhou | Jan. 21, 2022 08:15 |  | 319528 | LAB1-Group23 | Jan. 21, 2022 18:08 | 0 | 0 | Jan. 21, 2022 18:08 LAB1-Group23 Defect still exists in version 1.1
3639708 | 68227 | ATM Project | 16 | ATM_1-16 | 292216 | Bug |  |  | 63738 | 1.0 | MFT - Invalid PIN Extension (3rd time) | The function being tested: Invalid key extension The initial state: After input incorrect password, Request to re-enter PIN is being displayed Steps to reproduce the bug: turn on system -> insert card #1 -> input incorrect password -> input incorrect password -> input incorrect password -> input correct password 4.expected outcome: Original transaction completes successfully 5.actual output: After 3 times of input incorrect PIN, bank card has been retained, system shows “please contact bank" message. | 2 | In Progress | 3 | Normal |  |  |  |  | 319537 | Tianfan Zhou | 319537 | Tianfan Zhou | Jan. 21, 2022 08:21 |  | 319528 | LAB1-Group23 | Jan. 21, 2022 18:15 | 0 | 0 | Jan. 21, 2022 18:15 LAB1-Group23 Defect still exists in version 1.1
3640980 | 68227 | ATM Project | 17 | ATM_1-17 | 292216 | Bug |  |  | 63741 | 1.1 | MFT- Missing $ sign in the withdrawal checking menu | 1. The function being tested: Withdrawal 2. The initial state: System is on and customer has inserted card # 1 3. Steps to reproduce the bug: 1.Turn on system 2. Insert card #1 3.Withdrawal 4.Checking 4. Expected outcome: Display menu should display all the options with $ sign 5. Actual output: Missing $ sign in option 3 in the menu. | 1 | Open | 3 | Normal |  |  |  |  | 319528 | LAB1-Group23 | 319528 | LAB1-Group23 | Jan. 22, 2022 15:13 |  | 319537 | Tianfan Zhou | Jan. 26, 2022 17:37 | 0 | 0
3640987 | 68227 | ATM Project | 18 | ATM_1-18 | 292216 | Bug |  |  | 63738 | 1.0 | MFT-Withdrawal occurs at the insufficient balance in the ATM machine | 1. The function being tested: Withdrawal 2. The initial state: System is on and customer has inserted card # 1 and the ATM machine has the balance of $100. 3. Steps to reproduce the bug: 1. Turn on system 2. Insert card #1 3. Withdrawal 4. Checking 5. Select $200 in the menu 4. Expected outcome: Should display insufficient balance on the display. 5. Actual output: Withdraws $20 from the checking account. | 3 | Resolved | 3 | Normal |  |  |  |  | 319528 | LAB1-Group23 | 319528 | LAB1-Group23 | Jan. 22, 2022 15:31 |  | 319528 | LAB1-Group23 | Jan. 22, 2022 15:35 | 0 | 0 | Jan. 22, 2022 15:32 LAB1-Group23 Defect has been resolved in version 1.1
3654589 | 68227 | ATM Project | 19 | ATM_1-19 | 292216 | Bug |  |  | 63738 | 1.0 | Error on Balance Inquiry with Money Market Account | 1. The function being tested: Balance Inquiry 2. The initial state: System is on and idle 3. Steps to reproduce the bug: turn on system -> insert card #1 -> Balance Inquiry->Money Market 4.expected outcome: It should show an invalid account type 5.actual output: It shows unknown error and dispenses $500 from any random account. | 3 | Resolved | 3 | Normal |  |  |  |  | 319528 | LAB1-Group23 | 319528 | LAB1-Group23 | Jan. 27, 2022 10:47 |  | 319528 | LAB1-Group23 | Jan. 27, 2022 11:13 | 0 | 0 | Jan. 27, 2022 10:47 LAB1-Group23 Defect has been resolved in version 1.1 but still exists in version 1.0
3654595 | 68227 | ATM Project | 20 | ATM_1-20 | 292216 | Bug |  |  |  |  | Spelling error | 1. The function being tested: Balance Inquiry 2. The initial state: System is on and idle 3. Steps to reproduce the bug: turn on system -> insert card #1 -> Balance Inquiry->Checking 4.expected outcome: After the transaction, It should display the message "Would you like to do another transaction?" 5.actual output: It displays the message "Wood you like to do another transaction?" | 3 | Resolved | 3 | Normal | 63738 | 1.0 |  |  | 319528 | LAB1-Group23 | 319528 | LAB1-Group23 | Jan. 27, 2022 10:52 |  | 319528 | LAB1-Group23 | Jan. 27, 2022 10:53 | 0 | 0 | Jan. 27, 2022 10:53 LAB1-Group23 Defect has been resolved in version 1.1 but still exists in version 1.0
3654605 | 68227 | ATM Project | 21 | ATM_1-21 | 292216 | Bug |  |  | 63738 | 1.0 | Error on deposit receipt | 1. The function being tested: Deposit 2. The initial state: System is on and idle 3. Steps to reproduce the bug: turn on system -> insert card #1 -> Deposit-> Checking 4.expected outcome: When a deposit is made. Total balance and Available Balance should be same on the receipt. 5.actual output: When a deposit is made. Total balance and Available Balance does not match on the receipt. | 2 | In Progress | 3 | Normal |  |  |  |  | 319528 | LAB1-Group23 | 319528 | LAB1-Group23 | Jan. 27, 2022 10:59 |  | 319528 | LAB1-Group23 | Jan. 27, 2022 11:00 | 0 | 0 | Jan. 27, 2022 11:00 LAB1-Group23 Defect still exists in version 1.1